## Budget - Consultation
Project Budget
Approved Budget Changes
|  | Project Name |  |  |  | Reason | Plan or CR ID | Changes Cost | Changes Revenue
Client
Contract start date
Contract end date
Contract duration
|  | Contract Type | FS
Scope
|  | Support start and end dates | 2027-05-18 | 2028-05-17
Progress
| (1) | Total Mandays |  |  |  | Total Changes on Budget
| Approved Project Budget |  |  |  |  | Final Budget (SAR)
| (2) | Total Estimated Cost ($) |  |  |  | Total Cost after changes
| (3) | Total Estimated Cost (SAR) |  |  |  | Total Revenue after changes
| (4) | Total Revenue |  | 6641250 | 10312459 | Budget Profit (SAR)
| (5) | Budget Profit (SAR) |  |  |  | Budget Profit (%)
| (6) | Budget Profit (%)
Estimated MD cost (SAR)
Estimated MD Price (SAR)
Invoices Schedule
| # | Invoiced Item | Planned Date | Invoice Value | Business Line | Status
| 1 |  |  |  | License
| 2 |  |  |  | Service
| 3 |  |  |  | 3rd Party
4
5
6
7
8
9
10

## Budget - Development
Project Budget
Approved Budget Changes
|  | Project Name | Abdelrahman Doghish |  |  | Reason | Plan or CR ID | Changes Cost | Changes Revenue
|  | Client |  |  |  | Third party license |  |  | -420000
|  | Contract start date |  |  |  | Outsystems license |  |  | -3960000
Contract end date
Contract duration
|  | Contract Type | FS
Scope
|  | Support start and end dates | 2027-05-18 | 2028-05-17
Progress
| (1) | Total Mandays |  |  |  | Total Changes on Budget
| Approved Project Budget |  |  |  |  | Final Budget (SAR)
| (2) | Total Estimated Cost ($) |  |  |  | Total Cost after changes
| (3) | Total Estimated Cost (SAR) |  |  |  | Total Revenue after changes
| (4) | Total Revenue |  | 20570344 |  | Budget Profit (SAR)
| (5) | Budget Profit (SAR) |  |  |  | Budget Profit (%)
| (6) | Budget Profit (%)
Estimated MD cost (SAR)
Estimated MD Price (SAR)
Invoices Schedule
| # | Invoiced Item | Planned Date | Invoice Value | Business Line | Status
| 1 |  |  |  | License
| 2 |  |  |  | Service
| 3 |  |  |  | 3rd Party
4
5
6
7
8
9
10

## Budget - Support
Project Budget
Approved Budget Changes
|  | Project Name |  |  |  | Reason | Plan or CR ID | Changes Cost | Changes Revenue
Client
Contract start date
Contract end date
Contract duration
|  | Contract Type | FS
Scope
|  | Support start and end dates | 2027-05-18 | 2028-05-17
Progress
| (1) | Total Mandays |  | 528 |  | Total Changes on Budget |  | 0 | 0
| Approved Project Budget |  |  |  |  | Final Budget (SAR)
| (2) | Total Estimated Cost ($) |  |  |  | Total Cost after changes
| (3) | Total Estimated Cost (SAR) |  |  |  | Total Revenue after changes
| (4) | Total Revenue |  | 2079000 |  | Budget Profit (SAR)
| (5) | Budget Profit (SAR) |  |  |  | Budget Profit (%)
| (6) | Budget Profit (%)
Estimated MD cost (SAR)
Estimated MD Price (SAR)
Invoices Schedule
| # | Invoiced Item | Planned Date | Invoice Value | Business Line | Status
| 1 |  |  |  | License
| 2 |  |  |  | Service
| 3 |  |  |  | 3rd Party
4
5
6
7
8
9
10

## Profitability - Development
Project Name |  |  |  |  | PM Name
Contract Start Date |  |  |  |  | Contract End Date |  |  |  | Current Scope
Support Start Date |  |  |  |  | Support End Date
Licenses and 3rd party Revenue |  |  |  |  | Licenses and 3rd party Cost
|  | Presales Budget |  |  | Current Month calculations | [9 empty] | Cost Variance |  |  | Profitability |  |  | Profit Variance |  | Progress and Virtual Invoices for fixed cost
Month | Consumed Revenue | Total Revenue (SAR) | Total Estimated Cost (SAR) | Estimated Effort MDs | This month MDs | Actual Effort to Date (MD) | % Completion from plan | Current Cost (SAR) | Estimated Remaining (MD) | EAC MDs | Expected overrun (SAR) | Revenue to date | Estimated Cost to Complete | Estimate at Completion | CPI | Variance | Variance (%) | Profit at Completion | Planned Profit | Profit at Completion (%) | Profitability Variance | Profitability Variance (%) | Total Issued Invoices (SAR) | Progress % | Total Recognized Revenue | Production | Accumulative virtual invoice | This month Virtual Invoice | VI+Issued
[8 empty] | (7) | (8) |  |  |  | (9) | (10) |  | (11) | (12) | (13) |  | (14) | (15) | (16) | (17) | (18) | (19)
2026-03-21 |  | 16190344 | 10257885 | 6556 |  |  | 1% | 32032 | 6556 | 6529.0833 | -58.94% | 161903.44 | 6746253.3947 | [5 empty] | 36.64% |  |  |  |  | 0.4089% | 161903.44 | 161903.44 | 161903.44 | 161903.44 | 161903.44
2026-04-21 | [6 empty] | 3%
Note on L6: Alya Rabea: If overrun is +ve: the project is running out of budget If overrun is -ve: we're within budget
Note on H9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to revisit
Note on AA9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please Correct

## Current Effort - Development
Fill in Yellow Cells with current Team Effort
[5 empty] | March |  |  | April |  |  | May |  |  | June |  |  | July |  |  | August |  |  | September |  |  | October |  |  | November |  |  | December |  |  | January
# | Name | Position | Hour Rate ($) | Overtime Rate | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Total Cost | Current MDs done
1 | Abdelrhman Doghish | KSA - Project Manager |  |  | 8 |  |  | 88
2 | Ahmed Araby | EGY - Sr UX Designer | [5 empty] | 56
3 | Ahmed Mortdi | EGY - Software Engineer | [5 empty] | 44
4 | Basem Mohamed | EGY - Project Manager |  |  | 19 | 16 |  | 39
5 | David Magdy | EGY - Lead Software Engineer |  |  | 30 |  |  | 32
6 | Haitham Nabil | EGY - Sr Business Analyst | [5 empty] | 64
7 | Mahmoud Spahi | KSA - Solution Architect / Manager | [5 empty] | 46
8 | Menna Adel | EGY - Sr UX Designer | [5 empty] | 25
9 | Moatasem Hatem | EGY - Lead Business Analyst |  |  | 45 | 73 |  | 127.5
10 | Moatasem Hatem | EGY - Lead Business Analyst - onsite
11 | Mostafa Bekhet | EGY - Lead Software Engineer - onsite |  |  | 10 |  |  | 32
12 | Mustafa Mokhtar | EGY - Sr Business Analyst - onsite |  |  |  | 12
13 | Sandra Lateef Nashed Awad | EGY - Sr Business Analyst | [5 empty] | 67
Total Cost in SAR
Average Cost per MD

## Current Effort - Consultation
Fill in Yellow Cells with current Team Effort
[6 empty] | May |  |  | June |  |  | July |  |  | Augast |  |  |  | September |  |  | October |  |  | November |  |  | December |  |  | January |  |  | February |  |  | March |  |  | April
# | Name |  | Position | Hour Rate ($) | Overtime Rate | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Total Cost | Current MDs done
1 | Abdelrhman Doghish |  | KSA - Project Manager | [5 empty] | 56 |  |  | 96 |  |  | 128 |  |  | 168 |  |  | 168 | [5 empty] | 136 |  |  | 128 |  |  | 104 | 36 |  |  | 84 |  | 80
2 | Talal Abdulwahed |  | KSA - Solution Architect / Manager | [5 empty] | 56 |  |  | 152 |  |  | 160 |  |  | 160 |  |  | 160 | [5 empty] | 136 |  |  | 168 |  |  | 104 | 36 |  | 40 | 94.5 |  | 149
3 | Abeer AbdelHameed |  | EGY - Business Analyst - onsite | [5 empty] | 52 |  | 8 | 168 |  | 16 | 167 |  |  | 144 |  |  |  |  | 8
4 | Abeer AbdelHameed |  | EGY - Sr Business Analyst - onsite | [28 empty] | 4 | 104 | 36 |  | 48 |  | 16.5
| Abeer AbdelHameed |  | EGY - Sr Business Analyst
5 | Ahmed Araby |  | EGY - Sr UX Designer
6 | Amr Ahmed |  | EGY - Sr UX Designer | [17 empty] | 16 |  |  | 13
7 | Bushra ElGhamdi |  | KSA - Business Analyst | [5 empty] | 80.5 |  |  | 174 |  |  | 160 | [5 empty] | 152
8 | Bushra ElGhamdi |  | KSA- Sr Business Analyst | [26 empty] | 152 |  |  | 96 | 24 |  | 7 |  | 18.5 | 80
9 | Dina Said |  | EGY - Lead Business Analyst | [5 empty] | 3 |  |  | 122 |  |  | 5
10 | Emad Elgabri |  | KSA - Solution Architect / Manager | [8 empty] | 72 |  |  | 168 |  |  | 170 |  |  | 168 | [8 empty] | 152 |  |  | 88 | 36 |  | 40 | 84 |  | 152
11 | Kareem Waleed |  | EGY - Lead Business Analyst - onsite | [23 empty] | 197 |  |  |  |  | 8 | 97.5 | 24 |  | 16 | 77 |  | 91
| Kareem Waleed |  | EGY - Lead Business Analyst
12 | Menna Adel |  | EGY - Sr UX Designer | [14 empty] | 40 |  |  | 18 |  |  | 75 |  |  | 176 |  |  | 48 |  |  | 30 |  |  |  | 30
13 | Mohammad Nabil |  | EGY - Project Manager | [33 empty] | 6 |  | 4
14 | Mohamed Abdallah |  | KSA - Project Manager | [8 empty] | 110 |  |  | 44
15 | Mohamed Eldegwy |  | EGY - Lead UX Designer | [14 empty] | 24 |  |  | 32 |  |  | 18
16 | Mohamed Foad |  | KSA - Solution Architect / Manager |  |  |  |  | 31 |  |  | 13 |  |  | 8.5 |  |  | 21.5 | [8 empty] | 24
17 | Khaled Elbialy |  | EGY - Sr Business Analyst - onsite | [14 empty] | 138 |  |  |  |  | 8 |  |  |  | 96 |  |  |  |  | 8 | 95 | 36 |  | 36 | 84 |  | 56
| Khaled Elbialy |  | EGY - Sr Business Analyst
18 | Moahmed Ismail |  | KSA - Solution Architect / Manager | [8 empty] | 58 |  |  | 149 |  |  | 144 |  |  | 116 |  |  | 101 |  |  | 121 |  |  | 104 |  |  | 32 |  |  |  | 18
19 | Mostafa Mokhtar |  | EGY - Sr. Software Engineer - onsite | [32 empty] | 1 | 1 |  | 1
20 | Shady Mahfouz |  | EGY - Business Analyst - onsite | [11 empty] | 6 |  |  | 180 |  |  |  |  | 11 | [8 empty] | 8 | 104 | 36 |  | 24 | 84
21 | Shady Mahfouz |  | EGY - Business Analyst | [35 empty] | 158
22 | Njoud ElMubarek |  | KSA - Business Analyst | [5 empty] | 88 |  |  | 176 |  |  | 120
Total Cost in SAR
Average Cost per MD
|  |  | 10 | 11
| Abdelrhman Doghish | 112.25 | 176 | 168
| Talal Abdulwahed | 112.25 | 176 | 168
| Abeer AbdelHameed | 45.215 | 176 | 168
| Bushra ElGhamdi | 56.25 | 176 | 168
| Emad Elgabri | 112.25 | 176 | 168
| Khaled Elbialy | 51.6313 | 176 | 168
| Moahmed Ismail | 112.25 | 176 | 168
| Shady Mahfouz | 45.215 | 176 | 168
| Mohamed Foad | 168.4 | 166

## Profitability - Consultation
Project Name |  |  |  |  | PM Name
Contract Start Date |  |  |  |  | Contract End Date |  |  |  | Current Scope
Support Start Date |  |  |  |  | Support End Date
Licenses and 3rd party Revenue |  |  |  |  | Licenses and 3rd party Cost
|  | Presales Budget |  |  | Current Month calculations | [9 empty] | Cost Variance |  |  | Profitability |  |  | Profit Variance |  | Progress and Virtual Invoices for fixed cost
Month | Consumed Revenue | Total Revenue (SAR) | Total Estimated Cost (SAR) | Estimated Effort MDs | This month MDs | Actual Effort to Date (MD) | % Completion from plan | Current Cost (SAR) | Estimated Remaining (MD) | EAC MDs | Expected overrun (SAR) | Revenue to date | Estimated Cost to Complete | Estimate at Completion | CPI | Variance | Variance (%) | Profit at Completion | Planned Profit | Profit at Completion (%) | Profitability Variance | Profitability Variance (%) | Total Issued Invoices (SAR) | Progress % | Total Recognized Revenue | Production | Accumulative virtual invoice | This month Virtual Invoice | VI+Issued
[8 empty] | (7) | (8) |  |  |  | (9) | (10) |  | (11) | (12) | (13) |  | (14) | (15) | (16) | (17) | (18) | (19)
2025-05-21 | [5 empty] | 3.88 | 1% | 19573.59 | [14 empty] | 0
2025-06-21 | [6 empty] | 2% | 121184.57 | [14 empty] | 0
2025-07-21 | [6 empty] | 8% | 454192.88 | [14 empty] | 0
2025-08-21 | [6 empty] | 18% | 807937.0781 | [14 empty] | 0
2025-09-21 |  | 6641250 | 4811400 | 1848 | 166.25 |  | 25% | 1224457.0594 | 1678.25 |  |  | 1660312.5 | 4111431.9068 | 5335888.9661 | 0.90171 | -524488.9661 | -7.897% | 1305361.0339 | 27.55% | 19.66% | -524488.9661 | -7.897% | 0
2025-10-21 |  | 6641250 | 4811400 | 1848 | 168 |  | 35% | 1616092.3875 | 1181 |  |  |  | 2857995.4847 | 4474087.8722 | 1.0754 | 337312.1278 | 5.079% | 2167162.1278 | 27.55% | 32.63% | 337312.1278 | 5.079% | 0 | 36.12% | 2324437.5 |  | 2324437.5
2025-11-21 |  | 6641250 | 4811400 | 1848 | 214.875 |  | 48% | 2067058.9125 | 955 |  |  |  | 2236398.7951 | 4303457.7076 | 1.118 | 507942.2924 | 7.648% | 2337792.2924 | 27.55% | 35.2% | 507942.2924 | 7.648% | 0 | 48.03% | 3187800 | 863362.5 | 3187800 |  | 3187800
2025-12-21 |  | 6641250 | 4811400 | 1848 | 188.125 |  | 58% | 2467746.075 | 755.6 | 1826.4175 | -0.0954% |  | 1741321.5986 | 4209067.6736 | 1.1431 | 602332.3264 | 9.07% | 2432182.3264 | 27.55% | 36.62% | 602332.3264 | 9.07% | 931607.14 | 58.63% | 3851925 | 664125 | 2920317.86 | -267482.14 | 3851925
2026-01-21 |  | 6641250 | 4811400 | 1848 | 169.375 |  | 66% | 2897830.7437 | 807.5 | 2047.6875 | 1.681% |  | 1886810.1199 | 4784640.8637 | 1.0056 | 26759.1363 | 0.4029% | 1856609.1363 | 27.55% | 27.96% | 26759.1363 | 0.4029% | 931607.14 | 60.57% | 4383225 | 531300 | 3451617.86 | 531300 | 4383225
2026-02-21 |  | 6641250 | 4811400 | 1848 |  |  | 62% | 3483382.1836 | 849 | 2205 | 18.35% |  | 2180967.1636 | 5664349.3472 | 0.84942 | -852949.3472 | -12.84% | 976900.6528 | 27.55% | 14.71% | -852949.3472 | -12.84% | 1863214.28 | 61.5% | 4117575 | -265650 | 2254360.72 | -1197257.14 | 4117575
2026-03-21 |  | 6641250 | 4811400 | 1848 |  | 1538.38 | 66% | 3903237 | 771.5 |  |  |  | 1954833.6548 | [5 empty] | 27.55% |  |  |  | 1863214.28 | 66.6% | 4383225 |  | 2520010.72 |  | 4383225
2026-04-21 |  | 6641250 | 4811400 | 1848 |  |  | 69%
Note on L6: Alya Rabea: If overrun is +ve: the project is running out of budget If overrun is -ve: we're within budget

## Help (hidden)
How to use this Cost Sheet
# | Column | Description
1 | Total Mandays | Total Project Mandays as per the estimation, proposal or contract
2 | Total Estimated Cost ($) | Estimated cost based on estimation (FP Projects) or No of resources (T&M projects) Generally, estimated cost = No of Mandays* Cost per Manday
3 | Total Estimated Cost (SAR) | Estimated Cost in SAR
4 | Total Revenue | Revenue as per contract
5 | Budget Profit (SAR) | Profit = Revenue - Estimated Cost
6 | Budget Profit (%) | Profit as a percentage of Revenue
7 | Current Cost (SAR) | Current Cost based on current team effort - according to rate per hour for every resource
8 | Estimated Remaining (MD) | Remaining mandays in the project based on baseline estimation (FPP) or contract (T&M)
9 | Estimated Cost to Complete | = Estimated Remaining Mandays * Cost per Manday
10 | Estimate at Completion | = Current Cost + Estimated Remaining
11 | Variance | = Total Estimated Cost - Estimate at Completion
12 | Variance (%) | Variance as a percentage of Total Cost
13 | Profit at Completion | = Total Revenue after CRs - Estimate at Completion
14 | Profit at Completion (%) | Profit at Completion as a percentage of Revenue
15 | Profitability Variance | = Profit at Completion - Baseline Profit (after CRs)
16 | Profitability Variance (%) | = Budget Profit % - Profit at Completion %
17 | Total issued invoices | All issued invoices for services only
18 | Progress % | The consumed cost from total EAC = Current Cost/ Estimat at completion
19 | Total Recognised Revenue | = progress% * Revenue According to actual effort done and progress of work, this is the amount of invoices I should issue, or the revenue I should receive.

## Estimated Cost (2) (hidden)
Put planned resources for the project and their positions to calculate Cost per month
Delivery Estimation
Name | Position | Hour Rate ($) | Actual Time (MH) | Onsite Rate ($) | Actual Time Onsite (MH) | Total Cost | Cost * Period | MD
Amr Elwitidi | KSA- Sr Business Analyst
Asmaa Ibrahim | EGY - Sr Business Analyst
Mohamed Abdallah | KSA - Project Manager
Abdessalem Hadad | KSA - Solution Architect
Ahmed Serag | KSA - Lead Software Engineer
Samah El Sayed | KSA - Lead Software Engineer
Aya Saeed | EGY - Sr. Software Engineer
Abdulrahman Abdallah | EGY - Sr. Software Engineer
Senior Software Developer | EGY - Sr. Software Engineer
Ahmed Gameel | EGY - Software Engineer
Mahmoud Sayed | EGY - Software Engineer
Fady Ayman | EGY - Software Engineer |  | 176
Rana Wael | EGY - Software Engineer
Youmna Mahmoud | EGY - Sr Quality Engineer
Yasmin Tarek | EGY - Quality Engineer
Ahmed Badawy | EGY - Quality Engineer
Mohamed Degwy | EGY - Sr UX Designer
Menna Adel | EGY - UX Designer |  | 176
UI DESIGNER | EGY - Sr UX Designer
Fill in below info from Contract:
TOTAL USD
Contract Period in months |  |  | TOTAL Estimated Cost SAR
No of Resources required
Total Mandays estimated for the project
Support Estimation
Name | Position | Hour Rate ($) | Actual Time (MH) | Onsite Rate ($) | Actual Time Onsite (MH) | Total Cost | MD
Fill in below info from Contract:
TOTAL USD per month (22 days)
Contract Period in months | 0 |  | TOTAL Estimated Cost per month (22 days) SAR
No of Resources required |  |  | TOTAL Estimated Cost per Day SAR
Total Mandays estimated for the project |  |  | Cost for 7 months

## Estimated Cost - Development
Position | Hour Rate ($) | Actual Time (MH) | Cost per month | Estimated # of Months | Total cost USD | Total No of MDs | Column1
KSA - Project Manager |  | 176 |  | 16
EGY - Lead Software Engineer |  | 176 |  | 16
KSA - Lead Software Engineer |  | 176 |  | 16
KSA - Sr. Software Engineer |  | 176 |  | 16
KSA - Sr. Software Engineer |  | 176 |  | 16
KSA - Software Engineer |  | 176 |  | 16
EGY - Sr. Software Engineer |  | 176 |  | 16
EGY - Sr. Software Engineer |  | 176 |  | 16
EGY - Software Engineer |  | 176 |  | 16
EGY - Software Engineer |  | 176 |  | 16
EGY - Software Engineer |  | 176 |  | 16
EGY - Software Engineer |  | 176 |  | 16
EGY - Software Engineer |  | 176 |  | 16
KSA- Sr Business Analyst |  | 176 |  | 15
KSA- Sr Business Analyst |  | 176 |  | 15
EGY - Sr Quality Engineer |  | 176 |  | 15
EGY - Sr Quality Engineer |  | 176 |  | 15
EGY - Sr UX Designer |  | 176 |  | 12
KSA - Sr. Technical Support |  | 176 |  | 6
KSA - Sr. Software Engineer |  | 176 |  | 12
TOTAL USD per month (22 days)
TOTAL Estimated Cost per month (22 days) SAR
Estimated MDs / Month
TOTAL Estimated Cost per MD SAR
Total project estimated Cost (SAR)

## Estimated Cost - Consultation
Position | Hour Rate ($) | Actual Time (MH) | Cost per month | Estimated # of Months | Total cost USD | Total No of MDs | Column1
KSA - Solution Architect / Manager |  | 176 |  | 12
KSA - Solution Architect / Manager |  | 176 |  | 3
KSA - Solution Architect / Manager |  | 176 |  | 3
KSA - Solution Architect / Manager |  | 176 |  | 3
KSA - Solution Architect / Manager |  | 176 |  | 3
KSA - Solution Architect / Manager |  | 176 |  | 12
KSA- Sr Business Analyst |  | 176 |  | 12
KSA- Sr Business Analyst |  | 176 |  | 12
KSA - Business Analyst |  | 176 |  | 12
KSA - Business Analyst |  | 176 |  | 12
TOTAL USD per month (22 days)
TOTAL Estimated Cost per month (22 days) SAR
Estimated MDs / Month
TOTAL Estimated Cost per MD SAR
Total project estimated Cost (SAR)
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10 as pre sales or 12 as phase duration?

## Estimated Cost - Support
Position | Hour Rate ($) | Actual Time (MH) | Cost per month | Estimated # of Months | Total cost USD | Total No of MDs | Column1
KSA - Technical Support |  | 176 |  | 12
KSA - Sr. Technical Support |  | 176 |  | 12
TOTAL USD per month (22 days)
TOTAL Estimated Cost per month (22 days) SAR
Estimated MDs / Month
TOTAL Estimated Cost per MD SAR
Total project estimated Cost (SAR)

## Positions2024 (hidden)
Position | Hour Rate | MD Rate | Tunis Rates
KSA - Technical Support |  | 450 | Name | Hour Rate
KSA - Sr. Technical Support |  | 633 | Tarek GUIZANI | 21.3
KSA - Software Engineer |  | 450 | SOUHAIL HAJRI | 21.3
KSA - Sr. Software Engineer |  | 633 | Houda BOUZAZI | 14.7
KSA - Lead Software Engineer |  | 696 | Marwen Reguigui | 31
KSA - Business Analyst |  | 450 | Emna ZOUAOUI | 13.3
KSA- Sr Business Analyst |  | 633 | Safouene ZID | 25.8
KSA - Lead Business Analyst |  | 696 | Khoubaieb GHAOUARI | 19.3
KSA - Solution Architect / Manager |  | 898 | Rafeh ZEKRI | 12.8
KSA - Project Manager |  | 898 | Samia ACHOURI | 25.8
EGY - Software Engineer |  | 223 | Achraf SALMI | 19.3
EGY - Sr. Software Engineer |  | 253 | Zein el Abidin TRABELSI | 25.8
EGY - Lead Software Engineer |  | 277 | Arafet ZOUARI | 16
EGY - Business Analyst |  | 223 | Sarra OUNISSI | 13.3
EGY - Sr Business Analyst |  | 235 | Aicha CHATTI | 25.8
EGY - Lead Business Analyst |  | 277 | Abir HAMMAMI | 19.3
EGY - Project Manager |  | 301 | Naiim BSILI | 21.3
EGY - Quality Engineer |  | 223 | IKbel BOUZRATI | 31
EGY - Sr Quality Engineer |  | 253 | Iheb MAATALI RIAHI | 26.5
EGY - Lead Quality Engineer |  | 277
EGY - UX Designer |  | 223
EGY - Sr UX Designer |  | 253
EGY - Lead UX Designer |  | 277
EGY - Software Engineer - onsite | 45.215
EGY - Sr. Software Engineer - onsite | 51.6313
EGY - Lead Software Engineer - onsite | 58.2987
EGY - Business Analyst - onsite | 45.215
EGY - Sr Business Analyst - onsite | 51.6313
EGY - Lead Business Analyst - onsite | 58.2987
EGY - Project Manager - onsite | 63.1313
EGY - Quality Engineer - onsite | 45.215
EGY - Sr Quality Engineer - onsite | 51.6313
EGY - Lead Quality Engineer - onsite | 58.2987
EGY - UX Designer - onsite | 45.215
EGY - Sr UX Designer - onsite | 51.6313
EGY - Lead UX Designer - onsite | 58.2987

## Positions (hidden)
Position | Hour Rate | MD Rate
KSA - Technical Support | 56 | 450
KSA - Sr. Technical Support | 79 | 633
KSA - Software Engineer | 56 | 450
KSA - Sr. Software Engineer | 79 | 633
KSA - Lead Software Engineer | 87 | 696
KSA - Business Analyst | 56 | 450
KSA- Sr Business Analyst | 79 | 633
KSA - Lead Business Analyst | 87 | 696
KSA - Solution Architect / Manager | 112 | 898
KSA - Project Manager | 112 | 898
EGY - Software Engineer | 28 | 223
EGY - Sr. Software Engineer | 32 | 253
EGY - Lead Software Engineer | 35 | 277
EGY - Business Analyst | 28 | 223
EGY - Sr Business Analyst | 29 | 235
EGY - Lead Business Analyst | 35 | 277
EGY - Project Manager | 38 | 301
EGY - Quality Engineer | 28 | 223
EGY - Sr Quality Engineer | 32 | 253
EGY - Lead Quality Engineer | 35 | 277
EGY - UX Designer | 28 | 223
EGY - Sr UX Designer | 32 | 253
EGY - Lead UX Designer | 35 | 277
EGY - Software Engineer - onsite | 45 | 361.72
EGY - Sr. Software Engineer - onsite | 52 | 413.05
EGY - Lead Software Engineer - onsite | 58 | 466.39
EGY - Business Analyst - onsite | 45 | 361.72
EGY - Sr Business Analyst - onsite | 52 | 413.05
EGY - Lead Business Analyst - onsite | 58 | 466.39
EGY - Project Manager - onsite | 63 | 505.05
EGY - Quality Engineer - onsite | 45 | 361.72
EGY - Sr Quality Engineer - onsite | 52 | 413.05
EGY - Lead Quality Engineer - onsite | 58 | 466.39
EGY - UX Designer - onsite | 45 | 361.72
EGY - Sr UX Designer - onsite | 52 | 413.05
EGY - Lead UX Designer - onsite | 58 | 466.39

## data (hidden)
USD to SAR rate | 3.75

## Positions2024
Position | Hour Rate | MD Rate | Tunis Rates
KSA - Technical Support |  | 450 | Name | Hour Rate
KSA - Sr. Technical Support |  | 633 | Tarek GUIZANI | 21.3
KSA - Software Engineer |  | 450 | SOUHAIL HAJRI | 21.3
KSA - Sr. Software Engineer |  | 633 | Houda BOUZAZI | 14.7
KSA - Lead Software Engineer |  | 696 | Marwen Reguigui | 31
KSA - Business Analyst |  | 450 | Emna ZOUAOUI | 13.3
KSA- Sr Business Analyst |  | 633 | Safouene ZID | 25.8
KSA - Lead Business Analyst |  | 696 | Khoubaieb GHAOUARI | 19.3
KSA - Solution Architect / Manager |  | 898 | Rafeh ZEKRI | 12.8
KSA - Project Manager |  | 898 | Samia ACHOURI | 25.8
EGY - Software Engineer |  | 223 | Achraf SALMI | 19.3
EGY - Sr. Software Engineer |  | 253 | Zein el Abidin TRABELSI | 25.8
EGY - Lead Software Engineer |  | 277 | Arafet ZOUARI | 16
EGY - Business Analyst |  | 223 | Sarra OUNISSI | 13.3
EGY - Sr Business Analyst |  | 235 | Aicha CHATTI | 25.8
EGY - Lead Business Analyst |  | 277 | Abir HAMMAMI | 19.3
EGY - Project Manager |  | 301 | Naiim BSILI | 21.3
EGY - Quality Engineer |  | 223 | IKbel BOUZRATI | 31
EGY - Sr Quality Engineer |  | 253 | Iheb MAATALI RIAHI | 26.5
EGY - Lead Quality Engineer |  | 277
EGY - UX Designer |  | 223
EGY - Sr UX Designer |  | 253
EGY - Lead UX Designer |  | 277
EGY - Software Engineer - onsite | 45.215
EGY - Sr. Software Engineer - onsite | 51.6313
EGY - Lead Software Engineer - onsite | 58.2987
EGY - Business Analyst - onsite | 45.215
EGY - Sr Business Analyst - onsite | 51.6313
EGY - Lead Business Analyst - onsite | 58.2987
EGY - Project Manager - onsite | 63.1313
EGY - Quality Engineer - onsite | 45.215
EGY - Sr Quality Engineer - onsite | 51.6313
EGY - Lead Quality Engineer - onsite | 58.2987
EGY - UX Designer - onsite | 45.215
EGY - Sr UX Designer - onsite | 51.6313
EGY - Lead UX Designer - onsite | 58.2987

## Tunis Rates
Name | Hour Rate
Tarek GUIZANI | 21.3
SOUHAIL HAJRI | 21.3
Houda BOUZAZI | 14.7
Marwen Reguigui | 31
Emna ZOUAOUI | 13.3
Safouene ZID | 25.8
Khoubaieb GHAOUARI | 19.3
Rafeh ZEKRI | 12.8
Samia ACHOURI | 25.8
Achraf SALMI | 19.3
Zein el Abidin TRABELSI | 25.8
Arafet ZOUARI | 16
Sarra OUNISSI | 13.3
Aicha CHATTI | 25.8
Abir HAMMAMI | 19.3
Naiim BSILI | 21.3
IKbel BOUZRATI | 31
Iheb MAATALI RIAHI | 26.5