## Budget - Consultation
Project Budget
Approved Budget Changes
|  | Project Name |  |  |  | Reason | Plan or CR ID | Changes Cost | Changes Revenue
Client
Contract start date
Contract end date
Contract duration
|  | Contract Type | FS
Scope
|  | Support start and end dates | 2027-05-18 | 2028-05-17
|  | Progress | 0%
| (1) | Total Mandays |  | 1848 |  | Total Changes on Budget |  | 0 | 0
| Approved Project Budget |  |  |  |  | Final Budget (SAR)
| (2) | Total Estimated Cost ($) |  | 1283040 |  | Total Cost after changes |  | 4811400
| (3) | Total Estimated Cost (SAR) |  | 4811400 |  | Total Revenue after changes |  | 6641250
| (4) | Total Revenue |  | 6641250 | 10312459 | Budget Profit (SAR) |  | 1829850
| (5) | Budget Profit (SAR) |  | 1829850 |  | Budget Profit (%) |  | 27.55%
| (6) | Budget Profit (%) |  | 27.55%
|  | Estimated MD cost (SAR) |  | 2603.5714
|  | Estimated MD Price (SAR) |  | 3593.75
Invoices Schedule
| # | Invoiced Item | Planned Date | Invoice Value | Business Line | Status
| 1 |  |  |  | License
| 2 |  |  |  | Service
| 3 |  |  |  | 3rd Party
4
5
6
7
8
9
10

## Budget - Development
Project Budget
Approved Budget Changes
|  | Project Name | Abdelrahman Doghish |  |  | Reason | Plan or CR ID | Changes Cost | Changes Revenue
|  | Client |  |  |  | Third party license |  |  | -420000
|  | Contract start date |  |  |  | Outsystems license |  |  | -3960000
Contract end date
Contract duration
|  | Contract Type | FS
Scope
|  | Support start and end dates | 2027-05-18 | 2028-05-17
|  | Progress | 0%
| (1) | Total Mandays |  | 6556 |  | Total Changes on Budget |  | 0 | -4380000
| Approved Project Budget |  |  |  |  | Final Budget (SAR)
| (2) | Total Estimated Cost ($) |  | 2735436 |  | Total Cost after changes |  | 10257885
| (3) | Total Estimated Cost (SAR) |  | 10257885 |  | Total Revenue after changes |  | 16190344
| (4) | Total Revenue |  | 20570344 |  | Budget Profit (SAR) |  | 5932459
| (5) | Budget Profit (SAR) |  | 10312459 |  | Budget Profit (%) |  | 36.64%
| (6) | Budget Profit (%) |  | 50.13%
|  | Estimated MD cost (SAR) |  | 1564.656
|  | Estimated MD Price (SAR) |  | 3137.6364
Invoices Schedule
| # | Invoiced Item | Planned Date | Invoice Value | Business Line | Status
| 1 |  |  |  | License
| 2 |  |  |  | Service
| 3 |  |  |  | 3rd Party
4
5
6
7
8
9
10

## Budget - Support
Project Budget
Approved Budget Changes
|  | Project Name |  |  |  | Reason | Plan or CR ID | Changes Cost | Changes Revenue
Client
Contract start date
Contract end date
Contract duration
|  | Contract Type | FS
Scope
|  | Support start and end dates | 2027-05-18 | 2028-05-17
|  | Progress | 0%
| (1) | Total Mandays |  | 528 |  | Total Changes on Budget |  | 0 | 0
| Approved Project Budget |  |  |  |  | Final Budget (SAR)
| (2) | Total Estimated Cost ($) |  | 285912 |  | Total Cost after changes |  | 1072170
| (3) | Total Estimated Cost (SAR) |  | 1072170 |  | Total Revenue after changes |  | 2079000
| (4) | Total Revenue |  | 2079000 |  | Budget Profit (SAR) |  | 1006830
| (5) | Budget Profit (SAR) |  | 1006830 |  | Budget Profit (%) |  | 48.43%
| (6) | Budget Profit (%) |  | 48.43%
|  | Estimated MD cost (SAR) |  | 2030.625
|  | Estimated MD Price (SAR) |  | 3937.5
Invoices Schedule
| # | Invoiced Item | Planned Date | Invoice Value | Business Line | Status
| 1 |  |  |  | License
| 2 |  |  |  | Service
| 3 |  |  |  | 3rd Party
4
5
6
7
8
9
10

## Profitability - Development
Project Name |  |  |  |  | PM Name
Contract Start Date |  |  |  |  | Contract End Date |  |  |  | Current Scope
Support Start Date |  |  |  |  | Support End Date
Licenses and 3rd party Revenue |  |  |  |  | Licenses and 3rd party Cost
|  | Presales Budget |  |  | Current Month calculations | [9 empty] | Cost Variance |  |  | Profitability |  |  | Profit Variance |  | Progress and Virtual Invoices for fixed cost
Month | Consumed Revenue | Total Revenue (SAR) | Total Estimated Cost (SAR) | Estimated Effort MDs | This month MDs | Actual Effort to Date (MD) | % Completion from plan | Current Cost (SAR) | Estimated Remaining (MD) | EAC MDs | Expected overrun (SAR) | Revenue to date | Estimated Cost to Complete | Estimate at Completion | CPI | Variance | Variance (%) | Profit at Completion | Planned Profit | Profit at Completion (%) | Profitability Variance | Profitability Variance (%) | Total Issued Invoices (SAR) | Progress % | Total Recognized Revenue | Production | Accumulative virtual invoice | This month Virtual Invoice | VI+Issued
[8 empty] | (7) | (8) |  |  |  | (9) | (10) |  | (11) | (12) | (13) |  | (14) | (15) | (16) | (17) | (18) | (19)
2026-03-21 |  | 16190344 | 10257885 | 6556 | 30.8333 | 30.8333 | 1% | 32032 | 6556 | 6529.0833 | -58.94% | 161903.44 | 6746253.3947 | 6778285.3947 | 1.5133 | 3479599.6053 | 21.49% | 9412058.6053 | 36.64% | 58.13% | 7582208.6053 | 30.58% |  | 0.4089% | 161903.44 | 161903.44 | 161903.44 | 161903.44 | 161903.44
2026-04-21 |  | 16190344 | 10257885 | 6556 | 77.5625 | 108.3958 | 3% | 150282.4125 |  | 6447.6042 | -44.89% | 485710.32 | 0 | 150282.4125 | 68.2574 | 10107602.5875 | 62.43% | 16040061.5875 | 36.64% | 99.07% | 14210211.5875 | 71.52% |  | 100% | 485710.32 | 485710.32 | 485710.32 | 485710.32 | 485710.32
Note on L6: Alya Rabea: If overrun is +ve: the project is running out of budget If overrun is -ve: we're within budget
Note on H9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to revisit
Note on AA9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please Correct

## Current Effort - Development
Fill in Yellow Cells with current Team Effort
[5 empty] | March |  |  | April |  |  | May |  |  | June |  |  | July |  |  | August |  |  | September |  |  | October |  |  | November |  |  | December |  |  | January
# | Name | Position | Hour Rate ($) | Overtime Rate | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Total Cost | Current MDs done
1 | Abdelrhman Doghish | KSA - Project Manager | 112.25 | 168.375 | 8 |  |  | 88 | [29 empty] | 10776 | 12
2 | Ahmed Araby | EGY - Sr UX Designer | 31.625 | 47.4375 |  |  |  | 56 | [29 empty] | 1771 | 7
3 | Ahmed Mortdi | EGY - Software Engineer | 27.875 | 41.8125 |  |  |  | 44 | [29 empty] | 1226.5 | 5.5
4 | Basem Mohamed | EGY - Project Manager | 37.625 | 56.4375 | 19 | 16 |  | 39 | [29 empty] | 2784.25 | 9.9167
5 | David Magdy | EGY - Lead Software Engineer | 34.625 | 51.9375 | 30 |  |  | 32 | [29 empty] | 2146.75 | 7.75
6 | Haitham Nabil | EGY - Sr Business Analyst | 29.375 | 44.0625 |  |  |  | 64 | [29 empty] | 1880 | 8
7 | Mahmoud Spahi | KSA - Solution Architect / Manager | 112.25 | 168.375 |  |  |  | 46 | [29 empty] | 5163.5 | 5.75
8 | Menna Adel | EGY - Sr UX Designer | 31.625 | 47.4375 |  |  |  | 25 | [29 empty] | 790.625 | 3.125
9 | Moatasem Hatem | EGY - Lead Business Analyst | 34.625 | 51.9375 | 45 | 73 |  | 127.5 | [29 empty] | 8500.4375 | 33.7292
10 | Moatasem Hatem | EGY - Lead Business Analyst - onsite | 58.2987 | 87.4481 | [33 empty] | 0 | 0
11 | Mostafa Bekhet | EGY - Lead Software Engineer - onsite | 58.2987 | 87.4481 | 10 |  |  | 32 | [29 empty] | 2448.5475 | 5.25
12 | Mustafa Mokhtar | EGY - Sr Business Analyst - onsite | 51.6313 | 77.4469 |  | 12 | [31 empty] | 619.575 | 2
13 | Sandra Lateef Nashed Awad | EGY - Sr Business Analyst | 29.375 | 44.0625 |  |  |  | 67 | [29 empty] | 1968.125 | 8.375
[7 empty] | 30.8333 |  |  | 77.5625 | [27 empty] | 40075.31 | 108.3958
834
|  |  |  | Total Cost in SAR | [7 empty] | 150282.4125
|  |  |  | Average Cost per MD | [7 empty] | 1386.4224

## Current Effort - Consultation
Fill in Yellow Cells with current Team Effort
[6 empty] | May |  |  | June |  |  | July |  |  | Augast |  |  |  | September |  |  | October |  |  | November |  |  | December |  |  | January |  |  | February |  |  | March |  |  | April
# | Name |  | Position | Hour Rate ($) | Overtime Rate | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Regular Time (MH) | Ramdan Hours | Over Time (MH) | Total Cost | Current MDs done
1 | Abdelrhman Doghish |  | KSA - Project Manager | 112.25 | 168.375 |  |  |  | 56 |  |  | 96 |  |  | 128 |  |  | 168 |  |  | 168 |  |  | 168 |  |  | 136 |  |  | 128 |  |  | 104 | 36 |  | 32 | 84 |  | 80 |  |  | 169722 | 178
2 | Talal Abdulwahed |  | KSA - Solution Architect / Manager | 112.25 | 168.375 |  |  |  | 56 |  |  | 152 |  |  | 160 |  |  | 160 |  |  | 160 |  |  | 168 |  |  | 136 |  |  | 168 |  |  | 104 | 36 |  | 40 | 94.5 |  | 149 |  |  | 196605.875 | 203.375
3 | Abeer AbdelHameed |  | EGY - Business Analyst - onsite | 45.215 | 67.8225 |  |  |  | 52 |  | 8 | 168 |  | 16 | 167 |  |  | 144 |  |  | 151 |  | 8 | 168 |  |  | 183 | [14 empty] | 48877.415 | 133.125
4 | Abeer AbdelHameed |  | EGY - Sr Business Analyst - onsite | 51.6313 | 77.4469 | [24 empty] | 125 |  | 4 | 104 | 36 |  | 48 | 75.5 | 16.5 | 114 |  |  | 33986.2703 | 70.0208
| Abeer AbdelHameed |  | EGY - Sr Business Analyst | 29.375 | 44.0625 | [33 empty] | 24.5 |  |  | 719.6875 | 3.0625
5 | Ahmed Araby |  | EGY - Sr UX Designer | 31.625 | 47.4375 | [18 empty] | 136 | [17 empty] | 4301 | 17
6 | Amr Ahmed |  | EGY - Sr UX Designer | 31.625 | 47.4375 | [15 empty] | 16 |  |  | 13 | [17 empty] | 917.125 | 3.625
7 | Bushra ElGhamdi |  | KSA - Business Analyst | 56.25 | 84.375 |  |  |  | 80.5 |  |  | 174 |  |  | 160 |  |  | 162 |  |  | 152 |  |  | 160 |  |  | 172 | [14 empty] | 59653.125 | 132.5625
8 | Bushra ElGhamdi |  | KSA- Sr Business Analyst | 79.125 | 118.6875 | [24 empty] | 152 |  |  | 96 | 24 |  | 7 | 78 | 18.5 | 80 |  |  | 48800.3438 | 61.1875
9 | Dina Said |  | EGY - Lead Business Analyst | 34.625 | 51.9375 |  |  |  | 3 |  |  | 122 |  |  | 5 | [26 empty] | 4501.25 | 16.25
10 | Emad Elgabri |  | KSA - Solution Architect / Manager | 112.25 | 168.375 | [6 empty] | 72 |  |  | 168 |  |  | 170 |  |  | 168 |  |  | 160 |  |  | 184 |  |  | 152 |  |  | 88 | 36 |  | 40 | 84 |  | 152 |  |  | 182518.5 | 189.25
11 | Kareem Waleed |  | EGY - Lead Business Analyst - onsite | 58.2987 | 87.4481 | [18 empty] | 204 |  |  | 197 |  |  | 138 |  | 8 | 97.5 | 24 |  | 16 | 77 |  | 91 |  |  | 57978.1069 | 110.7708
| Kareem Waleed |  | EGY - Lead Business Analyst | 34.625 | 51.9375 | [33 empty] | 80.5 |  |  | 2787.3125 | 10.0625
12 | Menna Adel |  | EGY - Sr UX Designer | 31.625 | 47.4375 | [12 empty] | 40 |  |  | 18 |  |  | 75 |  |  | 176 |  |  | 48 |  |  | 30 |  |  |  | 30 |  |  |  |  | 14705.625 | 53.375
13 | Mohammad Nabil |  | EGY - Project Manager | 37.625 | 56.4375 | [31 empty] | 6 |  | 4 |  |  | 376.25 | 1.5
14 | Mohamed Abdallah |  | KSA - Project Manager | 112.25 | 168.375 | [6 empty] | 110 |  |  | 44 | [26 empty] | 17286.5 | 19.25
15 | Mohamed Eldegwy |  | EGY - Lead UX Designer | 34.625 | 51.9375 | [12 empty] | 24 |  |  | 32 |  |  | 18 | [17 empty] | 2562.25 | 9.25
16 | Mohamed Foad |  | KSA - Solution Architect / Manager | 112.25 | 168.375 |  |  | 31 |  |  | 13 |  |  | 8.5 |  |  | 21.5 | [8 empty] | 24 | [15 empty] | 16500.75 | 12.25
17 | Khaled Elbialy |  | EGY - Sr Business Analyst - onsite | 51.6313 | 77.4469 | [12 empty] | 138 |  |  | 168 |  | 8 | 160 |  |  | 96 |  |  | 152 |  | 8 | 95 | 36 |  | 36 | 84 |  | 56 |  |  | 61802.6063 | 134.625
| Khaled Elbialy |  | EGY - Sr Business Analyst | 29.375 | 44.0625 | [33 empty] | 105 |  |  | 3084.375 | 13.125
18 | Moahmed Ismail |  | KSA - Solution Architect / Manager | 112.25 | 168.375 | [6 empty] | 58 |  |  | 149 |  |  | 144 |  |  | 116 |  |  | 101 |  |  | 121 |  |  | 104 |  |  | 32 |  |  |  | 18 |  |  |  |  | 106300.75 | 106.125
19 | Mostafa Mokhtar |  | EGY - Sr. Software Engineer - onsite | 51.6313 | 77.4469 | [30 empty] | 1 | 1 |  | 1 |  |  | 154.8938 | 0.41667
20 | Shady Mahfouz |  | EGY - Business Analyst - onsite | 45.215 | 67.8225 | [9 empty] | 6 |  |  | 180 |  |  | 168 |  | 11 | 164 |  |  | 104 |  |  | 160 |  | 8 | 104 | 36 |  | 24 | 84 |  |  |  |  | 55094.4775 | 136.125
21 | Shady Mahfouz |  | EGY - Business Analyst | 27.875 | 41.8125 | [33 empty] | 158 |  |  | 4404.25 | 19.75
22 | Njoud ElMubarek |  | KSA - Business Analyst | 56.25 | 84.375 |  |  |  | 88 |  |  | 176 |  |  | 120 | [26 empty] | 21600 | 48
[8 empty] | 3.875 |  |  | 44.5625 |  |  | 144.0625 |  |  | 141.0625 |  |  | 166.25 |  |  | 168 |  |  | 214.875 |  |  | 188.125 |  |  | 169.375 |  |  | 150.8125 |  |  | 154.2083 |  |  | 136.875 | 1115240.7384 | 1682.0833
[5 empty] | Total Cost in SAR | [7 empty] | 4182152.7691
[5 empty] | Average Cost per MD | [7 empty] | 2486.2934
|  |  | 10 | 11
| Abdelrhman Doghish | 112.25 | 176 | 168
| Talal Abdulwahed | 112.25 | 176 | 168
| Abeer AbdelHameed | 45.215 | 176 | 168
| Bushra ElGhamdi | 56.25 | 176 | 168
| Emad Elgabri | 112.25 | 176 | 168
| Khaled Elbialy | 51.6313 | 176 | 168
| Moahmed Ismail | 112.25 | 176 | 168
| Shady Mahfouz | 45.215 | 176 | 168
| Mohamed Foad | 168.4 | 166

## Profitability - Consultation
Project Name |  |  |  |  | PM Name
Contract Start Date |  |  |  |  | Contract End Date |  |  |  | Current Scope
Support Start Date |  |  |  |  | Support End Date
Licenses and 3rd party Revenue |  |  |  |  | Licenses and 3rd party Cost
|  | Presales Budget |  |  | Current Month calculations | [9 empty] | Cost Variance |  |  | Profitability |  |  | Profit Variance |  | Progress and Virtual Invoices for fixed cost
Month | Consumed Revenue | Total Revenue (SAR) | Total Estimated Cost (SAR) | Estimated Effort MDs | This month MDs | Actual Effort to Date (MD) | % Completion from plan | Current Cost (SAR) | Estimated Remaining (MD) | EAC MDs | Expected overrun (SAR) | Revenue to date | Estimated Cost to Complete | Estimate at Completion | CPI | Variance | Variance (%) | Profit at Completion | Planned Profit | Profit at Completion (%) | Profitability Variance | Profitability Variance (%) | Total Issued Invoices (SAR) | Progress % | Total Recognized Revenue | Production | Accumulative virtual invoice | This month Virtual Invoice | VI+Issued
[8 empty] | (7) | (8) |  |  |  | (9) | (10) |  | (11) | (12) | (13) |  | (14) | (15) | (16) | (17) | (18) | (19)
2025-05-21 |  | 6641250 | 4811400 | 1848 | 3.875 | 3.88 | 1% | 19573.59 | 1844.12 | 1848 | -79% | 66412.5 | 4585023.4717 | 4604597.0617 | 1.0449 | 206802.9383 | 3.114% | 2036652.9383 | 27.55% | 30.67% | 206802.9383 | 3.114% | 0 | 1% | 66412.5 | 66431.5 | 66412.5 | 66412.5 | 66412.5
2025-06-21 |  | 6641250 | 4811400 | 1848 | 44.5625 | 48.4425 | 2% | 121184.57 | 1799.5575 | 1848 | 31.07% | 132825 | 4474228.0199 | 4595412.5899 | 1.047 | 215987.4101 | 3.252% | 2045837.4101 | 27.55% | 30.81% | 215987.4101 | 3.252% | 0 | 2% | 132825 | 66412.5 | 132825 | 66412.5 | 132825
2025-07-21 |  | 6641250 | 4811400 | 1848 | 144.0625 | 192.505 | 8% | 454192.88 | 1655.495 | 1848 | 30.21% | 531300 | 4116046.3702 | 4570239.2502 | 1.0528 | 241160.7498 | 3.631% | 2071010.7498 | 27.55% | 31.18% | 241160.7498 | 3.631% | 0 | 8% | 531300 | 398475 | 531300 | 398475 | 531300
2025-08-21 |  | 6641250 | 4811400 | 1848 | 141.0625 | 333.5675 | 18% | 807937.0781 | 1514.4325 | 1848 | 0.2788% | 1195425 | 3765323.6008 | 4573260.6789 | 1.0521 | 238139.3211 | 3.586% | 2067989.3211 | 27.55% | 31.14% | 238139.3211 | 3.586% | 0 | 18% | 1195425 | 664125 | 1195425 | 664125 | 1195425
2025-09-21 |  | 6641250 | 4811400 | 1848 | 166.25 | 499.8175 | 25% | 1224457.0594 | 1678.25 | 2178.0675 | 8.186% | 1660312.5 | 4111431.9068 | 5335888.9661 | 0.90171 | -524488.9661 | -7.897% | 1305361.0339 | 27.55% | 19.66% | -524488.9661 | -7.897% | 0 | 22.95% | 1660312.5 | 464887.5 | 1660312.5 | 464887.5 | 1660312.5
2025-10-21 |  | 6641250 | 4811400 | 1848 | 168 | 667.8175 | 35% | 1616092.3875 | 1181 | 1848.8175 | 3.249% | 2324437.5 | 2857995.4847 | 4474087.8722 | 1.0754 | 337312.1278 | 5.079% | 2167162.1278 | 27.55% | 32.63% | 337312.1278 | 5.079% | 0 | 36.12% | 2324437.5 | 664125 | 2324437.5 | 664125 | 2324437.5
2025-11-21 |  | 6641250 | 4811400 | 1848 | 214.875 | 882.6925 | 48% | 2067058.9125 | 955 | 1837.6925 | -0.4901% | 3187800 | 2236398.7951 | 4303457.7076 | 1.118 | 507942.2924 | 7.648% | 2337792.2924 | 27.55% | 35.2% | 507942.2924 | 7.648% | 0 | 48.03% | 3187800 | 863362.5 | 3187800 | 863362.5 | 3187800
2025-12-21 |  | 6641250 | 4811400 | 1848 | 188.125 | 1070.8175 | 58% | 2467746.075 | 755.6 | 1826.4175 | -0.0954% | 3851925 | 1741321.5986 | 4209067.6736 | 1.1431 | 602332.3264 | 9.07% | 2432182.3264 | 27.55% | 36.62% | 602332.3264 | 9.07% | 931607.14 | 58.63% | 3851925 | 664125 | 2920317.86 | -267482.14 | 3851925
2026-01-21 |  | 6641250 | 4811400 | 1848 | 169.375 | 1240.1925 | 66% | 2897830.7437 | 807.5 | 2047.6875 | 1.681% | 4383225 | 1886810.1199 | 4784640.8637 | 1.0056 | 26759.1363 | 0.4029% | 1856609.1363 | 27.55% | 27.96% | 26759.1363 | 0.4029% | 931607.14 | 60.57% | 4383225 | 531300 | 3451617.86 | 531300 | 4383225 | 730537.5 | -2064283.64
2026-02-21 |  | 6641250 | 4811400 | 1848 | 150.8125 | 1391.005 | 62% | 3483382.1836 | 849 | 2205 | 18.35% | 4117575 | 2180967.1636 | 5664349.3472 | 0.84942 | -852949.3472 | -12.84% | 976900.6528 | 27.55% | 14.71% | -852949.3472 | -12.84% | 1863214.28 | 61.5% | 4117575 | -265650 | 2254360.72 | -1197257.14 | 4117575
2026-03-21 |  | 6641250 | 4811400 | 1848 | 154.2083 | 1538.38 | 66% | 3903237 | 771.5 | 2309.88 | 26.13% | 4383225 | 1954833.6548 | 5858070.6548 | 0.82133 | -1046670.6548 | -15.76% | 783179.3452 | 27.55% | 11.79% | -1046670.6548 | -15.76% | 1863214.28 | 66.6% | 4383225 | 265650 | 2520010.72 | 265650 | 4383225 | -2064283.64 | 730537.5
2026-04-21 |  | 6641250 | 4811400 | 1848 | 136.875 | 1682.0833 | 69% | 4182152.7691 |  | 1682.0833 | 31.92% | 4582462.5 | 0 | 4182152.7691 | 1.1505 | 629247.2309 | 9.475% | 2459097.2309 | 27.55% | 37.03% | 629247.2309 | 9.475% | 3726428.28 | 100% | 4582462.5 | 199237.5 | 856034.22 | -1663976.5 | 4582462.5
Note on L6: Alya Rabea: If overrun is +ve: the project is running out of budget If overrun is -ve: we're within budget

## Help (hidden)
How to use this Cost Sheet
# | Column | Description
1 | Total Mandays | Total Project Mandays as per the estimation, proposal or contract
2 | Total Estimated Cost ($) | Estimated cost based on estimation (FP Projects) or No of resources (T&M projects) Generally, estimated cost = No of Mandays* Cost per Manday
3 | Total Estimated Cost (SAR) | Estimated Cost in SAR
4 | Total Revenue | Revenue as per contract
5 | Budget Profit (SAR) | Profit = Revenue - Estimated Cost
6 | Budget Profit (%) | Profit as a percentage of Revenue
7 | Current Cost (SAR) | Current Cost based on current team effort - according to rate per hour for every resource
8 | Estimated Remaining (MD) | Remaining mandays in the project based on baseline estimation (FPP) or contract (T&M)
9 | Estimated Cost to Complete | = Estimated Remaining Mandays * Cost per Manday
10 | Estimate at Completion | = Current Cost + Estimated Remaining
11 | Variance | = Total Estimated Cost - Estimate at Completion
12 | Variance (%) | Variance as a percentage of Total Cost
13 | Profit at Completion | = Total Revenue after CRs - Estimate at Completion
14 | Profit at Completion (%) | Profit at Completion as a percentage of Revenue
15 | Profitability Variance | = Profit at Completion - Baseline Profit (after CRs)
16 | Profitability Variance (%) | = Budget Profit % - Profit at Completion %
17 | Total issued invoices | All issued invoices for services only
18 | Progress % | The consumed cost from total EAC = Current Cost/ Estimat at completion
19 | Total Recognised Revenue | = progress% * Revenue According to actual effort done and progress of work, this is the amount of invoices I should issue, or the revenue I should receive.
2 - Budget Sheet
3 - Current Effort Sheet
4 - Profitability Sheet
1- Estimated Cost sheet
Budget Planning

## Estimated Cost (2) (hidden)
Put planned resources for the project and their positions to calculate Cost per month
Delivery Estimation
Name | Position | Hour Rate ($) | Actual Time (MH) | Onsite Rate ($) | Actual Time Onsite (MH) | Total Cost | Cost * Period | MD
Amr Elwitidi | KSA- Sr Business Analyst | 72.5 | 176 | 91.5 |  | 12760 | 102080 | 176
Asmaa Ibrahim | EGY - Sr Business Analyst | 22.375 | 176 | 41.375 |  | 3938 | 15752 | 88
Mohamed Abdallah | KSA - Project Manager | 78.25 | 176 | 97.25 |  | 13772 | 123948 | 198
Abdessalem Hadad | KSA - Solution Architect | 96.75 | 176 | 115.75 |  | 17028 | 17028 | 22
Ahmed Serag | KSA - Lead Software Engineer | 70.25 | 176 | 89.25 |  | 12364 | 98912 | 176
Samah El Sayed | KSA - Lead Software Engineer | 70.25 | 176 | 89.25 |  | 12364 | 86548 | 154
Aya Saeed | EGY - Sr. Software Engineer | 20 | 176 | 39 |  | 3520 | 24640 | 154
Abdulrahman Abdallah | EGY - Sr. Software Engineer | 20 | 176 | 39 |  | 3520 | 28160 | 176
Senior Software Developer | EGY - Sr. Software Engineer | 20 | 176 | 39 |  | 3520 | 21120 | 132
Ahmed Gameel | EGY - Software Engineer | 17.625 | 176 | 36.625 |  | 3102 | 21714 | 154
Mahmoud Sayed | EGY - Software Engineer | 17.625 | 176 | 36.625 |  | 3102 | 15510 | 110
Fady Ayman | EGY - Software Engineer | 17.625 | 176 | 36.625 |  | 3102 | 12408 | 132
Rana Wael | EGY - Software Engineer | 17.625 | 176 | 36.625 |  | 3102 | 18612 | 88
Youmna Mahmoud | EGY - Sr Quality Engineer | 19 | 176 | 38 |  | 3344 | 26752 | 176
Yasmin Tarek | EGY - Quality Engineer | 14.25 | 176 | 33.25 |  | 2508 | 17556 | 154
Ahmed Badawy | EGY - Quality Engineer | 14.25 | 176 | 33.25 |  | 2508 | 17556 | 154
Mohamed Degwy | EGY - Sr UX Designer | 22.375 | 176 | 41.375 |  | 3938 | 7876 | 44
Menna Adel | EGY - UX Designer | 15.25 | 176 | 34.25 |  | 2684 | 8052 | 88
UI DESIGNER | EGY - Sr UX Designer | 22.375 | 176 | 41.375 |  | 3938 | 23628 | 132
2508
Fill in below info from Contract:
|  |  | TOTAL USD |  |  | 687852
Contract Period in months |  |  | TOTAL Estimated Cost SAR |  |  | 2579445
No of Resources required
Total Mandays estimated for the project
Support Estimation
Name | Position | Hour Rate ($) | Actual Time (MH) | Onsite Rate ($) | Actual Time Onsite (MH) | Total Cost | MD
Fill in below info from Contract:
|  |  | TOTAL USD per month (22 days) |  |  | 0
Contract Period in months | 0 |  | TOTAL Estimated Cost per month (22 days) SAR |  |  | 0
No of Resources required | 0 |  | TOTAL Estimated Cost per Day SAR |  |  | 0
Total Mandays estimated for the project | 0 |  | Cost for 7 months |  |  | 0

## Estimated Cost - Development
Position | Hour Rate ($) | Actual Time (MH) | Cost per month | Estimated # of Months | Total cost USD | Total No of MDs | Column1
KSA - Project Manager | 112.25 | 176 | 19756 | 16 | 316096 | 352 | 1185360
EGY - Lead Software Engineer | 34.625 | 176 | 6094 | 16 | 97504 | 352 | 365640
KSA - Lead Software Engineer | 87 | 176 | 15312 | 16 | 244992 | 352 | 918720
KSA - Sr. Software Engineer | 79.125 | 176 | 13926 | 16 | 222816 | 352 | 835560
KSA - Sr. Software Engineer | 79.125 | 176 | 13926 | 16 | 222816 | 352 | 835560
KSA - Software Engineer | 56.25 | 176 | 9900 | 16 | 158400 | 352 | 594000
EGY - Sr. Software Engineer | 31.625 | 176 | 5566 | 16 | 89056 | 352 | 333960
EGY - Sr. Software Engineer | 31.625 | 176 | 5566 | 16 | 89056 | 352 | 333960
EGY - Software Engineer | 27.875 | 176 | 4906 | 16 | 78496 | 352 | 294360
EGY - Software Engineer | 27.875 | 176 | 4906 | 16 | 78496 | 352 | 294360
EGY - Software Engineer | 27.875 | 176 | 4906 | 16 | 78496 | 352 | 294360
EGY - Software Engineer | 27.875 | 176 | 4906 | 16 | 78496 | 352 | 294360
EGY - Software Engineer | 27.875 | 176 | 4906 | 16 | 78496 | 352 | 294360
KSA- Sr Business Analyst | 79.125 | 176 | 13926 | 15 | 208890 | 330 | 783337.5
KSA- Sr Business Analyst | 79.125 | 176 | 13926 | 15 | 208890 | 330 | 783337.5
EGY - Sr Quality Engineer | 31.625 | 176 | 5566 | 15 | 83490 | 330 | 313087.5
EGY - Sr Quality Engineer | 31.625 | 176 | 5566 | 15 | 83490 | 330 | 313087.5
EGY - Sr UX Designer | 31.625 | 176 | 5566 | 12 | 66792 | 264 | 250470
KSA - Sr. Technical Support | 79.125 | 176 | 13926 | 6 | 83556 | 132 | 313335
KSA - Sr. Software Engineer | 79.125 | 176 | 13926 | 12 | 167112 | 264 | 626670
[5 empty] | 2735436 | 6556
|  | TOTAL USD per month (22 days) | 186978
|  | TOTAL Estimated Cost per month (22 days) SAR | 701167.5
|  | Estimated MDs / Month | 440
|  | TOTAL Estimated Cost per MD SAR | 1593.5625
|  | Total project estimated Cost (SAR) | 10257885

## Estimated Cost - Consultation
Position | Hour Rate ($) | Actual Time (MH) | Cost per month | Estimated # of Months | Total cost USD | Total No of MDs | Column1
KSA - Solution Architect / Manager | 112.25 | 176 | 19756 | 12 | 237072 | 264 | 889020
KSA - Solution Architect / Manager | 112.25 | 176 | 19756 | 3 | 59268 | 66 | 222255
KSA - Solution Architect / Manager | 112.25 | 176 | 19756 | 3 | 59268 | 66 | 222255
KSA - Solution Architect / Manager | 112.25 | 176 | 19756 | 3 | 59268 | 66 | 222255
KSA - Solution Architect / Manager | 112.25 | 176 | 19756 | 3 | 59268 | 66 | 222255
KSA - Solution Architect / Manager | 112.25 | 176 | 19756 | 12 | 237072 | 264 | 889020
KSA- Sr Business Analyst | 79.125 | 176 | 13926 | 12 | 167112 | 264 | 626670
KSA- Sr Business Analyst | 79.125 | 176 | 13926 | 12 | 167112 | 264 | 626670
KSA - Business Analyst | 56.25 | 176 | 9900 | 12 | 118800 | 264 | 445500
KSA - Business Analyst | 56.25 | 176 | 9900 | 12 | 118800 | 264 | 445500
[5 empty] | 1283040 | 1848
|  | TOTAL USD per month (22 days) | 166188
|  | TOTAL Estimated Cost per month (22 days) SAR | 623205
|  | Estimated MDs / Month | 220
|  | TOTAL Estimated Cost per MD SAR | 2832.75 |  |  | 1293600
|  | Total project estimated Cost (SAR) | 4811400 |  |  | 4851000
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10 as pre sales or 12 as phase duration?

## Estimated Cost - Support
Position | Hour Rate ($) | Actual Time (MH) | Cost per month | Estimated # of Months | Total cost USD | Total No of MDs | Column1
KSA - Technical Support | 56.25 | 176 | 9900 | 12 | 118800 | 264 | 445500
KSA - Sr. Technical Support | 79.125 | 176 | 13926 | 12 | 167112 | 264 | 626670
[5 empty] | 285912 | 528
|  | TOTAL USD per month (22 days) | 23826
|  | TOTAL Estimated Cost per month (22 days) SAR | 89347.5
|  | Estimated MDs / Month | 44
|  | TOTAL Estimated Cost per MD SAR | 2030.625
|  | Total project estimated Cost (SAR) | 1072170

## Positions2024 (hidden)
Position | Hour Rate | MD Rate | Tunis Rates
KSA - Technical Support | 56.25 | 450 | Name | Hour Rate
KSA - Sr. Technical Support | 79.125 | 633 | Tarek GUIZANI | 21.3
KSA - Software Engineer | 56.25 | 450 | SOUHAIL HAJRI | 21.3
KSA - Sr. Software Engineer | 79.125 | 633 | Houda BOUZAZI | 14.7
KSA - Lead Software Engineer | 87 | 696 | Marwen Reguigui | 31
KSA - Business Analyst | 56.25 | 450 | Emna ZOUAOUI | 13.3
KSA- Sr Business Analyst | 79.125 | 633 | Safouene ZID | 25.8
KSA - Lead Business Analyst | 87 | 696 | Khoubaieb GHAOUARI | 19.3
KSA - Solution Architect / Manager | 112.25 | 898 | Rafeh ZEKRI | 12.8
KSA - Project Manager | 112.25 | 898 | Samia ACHOURI | 25.8
EGY - Software Engineer | 27.875 | 223 | Achraf SALMI | 19.3
EGY - Sr. Software Engineer | 31.625 | 253 | Zein el Abidin TRABELSI | 25.8
EGY - Lead Software Engineer | 34.625 | 277 | Arafet ZOUARI | 16
EGY - Business Analyst | 27.875 | 223 | Sarra OUNISSI | 13.3
EGY - Sr Business Analyst | 29.375 | 235 | Aicha CHATTI | 25.8
EGY - Lead Business Analyst | 34.625 | 277 | Abir HAMMAMI | 19.3
EGY - Project Manager | 37.625 | 301 | Naiim BSILI | 21.3
EGY - Quality Engineer | 27.875 | 223 | IKbel BOUZRATI | 31
EGY - Sr Quality Engineer | 31.625 | 253 | Iheb MAATALI RIAHI | 26.5
EGY - Lead Quality Engineer | 34.625 | 277
EGY - UX Designer | 27.875 | 223
EGY - Sr UX Designer | 31.625 | 253
EGY - Lead UX Designer | 34.625 | 277
EGY - Software Engineer - onsite | 45.215 | 361.72
EGY - Sr. Software Engineer - onsite | 51.6313 | 413.05
EGY - Lead Software Engineer - onsite | 58.2987 | 466.39
EGY - Business Analyst - onsite | 45.215 | 361.72
EGY - Sr Business Analyst - onsite | 51.6313 | 413.05
EGY - Lead Business Analyst - onsite | 58.2987 | 466.39
EGY - Project Manager - onsite | 63.1313 | 505.05
EGY - Quality Engineer - onsite | 45.215 | 361.72
EGY - Sr Quality Engineer - onsite | 51.6313 | 413.05
EGY - Lead Quality Engineer - onsite | 58.2987 | 466.39
EGY - UX Designer - onsite | 45.215 | 361.72
EGY - Sr UX Designer - onsite | 51.6313 | 413.05
EGY - Lead UX Designer - onsite | 58.2987 | 466.39

## Positions (hidden)
Position | Hour Rate | MD Rate
KSA - Technical Support | 37.625 | 301
KSA - Sr. Technical Support | 54.125 | 433
KSA - Software Engineer | 43.75 | 350
KSA - Sr. Software Engineer | 56.125 | 449
KSA - Lead Software Engineer | 70.25 | 562
KSA - Business Analyst | 37.625 | 301
KSA- Sr Business Analyst | 72.5 | 580
KSA - Lead Business Analyst | 80.375 | 643
KSA - Solution Architect | 96.75 | 774
KSA - Project Manager | 78.25 | 626
EGY - Software Engineer | 17.625 | 141
EGY - Sr. Software Engineer | 20 | 160
EGY - Lead Software Engineer | 26.25 | 210
EGY - Business Analyst | 17.625 | 141
EGY - Sr Business Analyst | 22.375 | 179
EGY - Lead Business Analyst | 26.75 | 214
EGY - Project Manager | 32 | 256
EGY - Quality Engineer | 14.25 | 114
EGY - Sr Quality Engineer | 19 | 152
EGY - Lead Quality Engineer | 25.75 | 206
EGY - UX Designer | 15.25 | 122
EGY - Sr UX Designer | 22.375 | 179
EGY - Lead UX Designer | 26.5 | 212

## data (hidden)
USD to SAR rate | 3.75

## Positions2024
Position | Hour Rate | MD Rate | Tunis Rates
KSA - Technical Support | 56.25 | 450 | Name | Hour Rate
KSA - Sr. Technical Support | 79.125 | 633 | Tarek GUIZANI | 21.3
KSA - Software Engineer | 56.25 | 450 | SOUHAIL HAJRI | 21.3
KSA - Sr. Software Engineer | 79.125 | 633 | Houda BOUZAZI | 14.7
KSA - Lead Software Engineer | 87 | 696 | Marwen Reguigui | 31
KSA - Business Analyst | 56.25 | 450 | Emna ZOUAOUI | 13.3
KSA- Sr Business Analyst | 79.125 | 633 | Safouene ZID | 25.8
KSA - Lead Business Analyst | 87 | 696 | Khoubaieb GHAOUARI | 19.3
KSA - Solution Architect / Manager | 112.25 | 898 | Rafeh ZEKRI | 12.8
KSA - Project Manager | 112.25 | 898 | Samia ACHOURI | 25.8
EGY - Software Engineer | 27.875 | 223 | Achraf SALMI | 19.3
EGY - Sr. Software Engineer | 31.625 | 253 | Zein el Abidin TRABELSI | 25.8
EGY - Lead Software Engineer | 34.625 | 277 | Arafet ZOUARI | 16
EGY - Business Analyst | 27.875 | 223 | Sarra OUNISSI | 13.3
EGY - Sr Business Analyst | 29.375 | 235 | Aicha CHATTI | 25.8
EGY - Lead Business Analyst | 34.625 | 277 | Abir HAMMAMI | 19.3
EGY - Project Manager | 37.625 | 301 | Naiim BSILI | 21.3
EGY - Quality Engineer | 27.875 | 223 | IKbel BOUZRATI | 31
EGY - Sr Quality Engineer | 31.625 | 253 | Iheb MAATALI RIAHI | 26.5
EGY - Lead Quality Engineer | 34.625 | 277
EGY - UX Designer | 27.875 | 223
EGY - Sr UX Designer | 31.625 | 253
EGY - Lead UX Designer | 34.625 | 277
EGY - Software Engineer - onsite | 45.215 | 361.72
EGY - Sr. Software Engineer - onsite | 51.6313 | 413.05
EGY - Lead Software Engineer - onsite | 58.2987 | 466.39
EGY - Business Analyst - onsite | 45.215 | 361.72
EGY - Sr Business Analyst - onsite | 51.6313 | 413.05
EGY - Lead Business Analyst - onsite | 58.2987 | 466.39
EGY - Project Manager - onsite | 63.1313 | 505.05
EGY - Quality Engineer - onsite | 45.215 | 361.72
EGY - Sr Quality Engineer - onsite | 51.6313 | 413.05
EGY - Lead Quality Engineer - onsite | 58.2987 | 466.39
EGY - UX Designer - onsite | 45.215 | 361.72
EGY - Sr UX Designer - onsite | 51.6313 | 413.05
EGY - Lead UX Designer - onsite | 58.2987 | 466.39